## Sheet1
Change Request ID | Description | Risks | Actions
change_request_1 | The client should have direct access to his/her only one account where he can view a history of previous transactions. | 1-Time delay to add new tasks 2-new Tasks will be added to the project which may impact the delivery. | SRS Change: 1-SRS_ View Account _002 2-SRS_ View Account _003 3-SRS_ View Account _004 4-update Add New Account in SRS. Design Change: 5-ViewClient_wireFrame_1 6-Low_Design_ViewAccountsList_Client_1 7-Low_Design_addAccount_client_1 8- classDiagram_viewAccount_Client_001 9- change client login sequence diagram code Change: 10-change code in view client class. 11- change frontend customer requirement change SIQ change RTM change these changes took 4 hours.
change_request_2 | Team member change | 1-Future tasks assignation (NONE) 2--Running tasks assignation (NONE) 3-Training needed for the new member 4-Training required from the old member (NONE) | 3- The new member is required to read the SRS to understand the application's features, also she needs to check the running application. Then the tasks will be assigned to her. -one of the members will run the application on the new member's laptop. -Expected time (5 hrs).