## SRS
Version | Comments | Reviewer | Status
Version 1 | update all features as per example created with coach. | Amr | Closed
Version 2 | add new account function | Mohamed Hassan | Closed
Version 2.1 | update add new account feature as per example created with coach. | Amr | Closed
Version 2.2 | update close account feature as per example created with coach. | Amr | Closed
Version 2.3 | update perform transaction feature as per example created with coach. | Amr | Closed
Version 2.4 | update register consistency between srs and code. | Hana | Closed
Version 2.4 | update login consistency between srs and code. | Hana | Closed
Version 2.4 | update view account consistency between srs and code. | Hana | Closed
Version 2.4 | update perform transaction consistency between srs and code. | Hana | Closed
Version 2.4 | update close account consistency between srs and code. | Hana | Closed
Version 2.5 | SRS_Login_003,SRS_Login_004,SRS_Login_005 are contradicting | Amr | Closed
Version 2.5 | SRS_ View Account _005 is useless | Amr | Closed
Version 2.5 | Description and Priority (Perform Transaction) need to say that this feature is part of view account page | Amr | Closed
Version 2.5 | SRS_PerformTransaction_003 what is meant by valid data | Amr | Closed
Version 2.5 | SRS_Add New Account _001 replace the message with "your account Number is <Newly Ceated Account Number> | Amr | Closed
Version 2.5 | SRS_Close Account _001 should enter an account that is present in the Database | Amr | Closed
Version 2.5 | SRS_Close Account _005 balance >0 | Amr | Closed
Version 2.5 | SRS_ Close Account _008 what is letter e | Amr | Closed

## Design Document
Version | Comments | Reviewer | Status
Version 1 | modify the naming convention of the designs | Hana | closed
Version 2 | there are missing designs | Hana | closed
Version 3 | there is no easy tracibility between function name in class diagram and the drawing need more sections to better descripe the design | Amr | closed
Version 5 | sequence diagrams are required to be generic not high level. | Amr
Version 5 | change IDs of navigation function flowchart from low level to high level | Amr

## Code
Version | Comments | Reviewer | Status
Version 1 | modify the functions as per mentioned in design document | Amr | Closed
Version 2 | put all functions related to client in one class and | Amr | Closed
Version 2 | put all function related to the admin in one class | Amr | Closed
Version 3 | add specific messages to transfer money, if user entered negative number | Mohamed Hassan | Closed
Version 3 | add specific messages to transfer money, if user entered zeros | Mohamed Hassan | Closed

## RTM
Version | Comments | Reviewer | Status
Version 1 |  | Amr
Version 2 | trans001 needs to be only linked to the part saying the attributes not the whole requirements? | Amr | closed
Version 3 | there are some missing diagrams | Hana | closed
Version 4 | add classes names in code beside each feature | Amr
Version 4 | add use case beside main functions | Amr
Version 4 | add erd beside any function related to database. | Amr
Version 4 | add wire frames | Amr